## Dashboard
OEE & TPM Loss Reduction — Executive Dashboard
High-Speed Packaging Line ¦ 12-Week Study ¦ Baseline -> Improved
BASELINE OEE (Wks 1-4) | IMPROVED OEE (Wks 9-12) | WORLD-CLASS TARGET | ANNUALIZED SAVINGS | CHANGEOVER TIME CUT
69.46% | 83.46% | 85% | 1917150.625 | 28.45
+14.0% pts

## Cover
OEE Improvement & TPM-Driven Loss Reduction
High-Speed Packaging Line ¦ Manufacturing Excellence / Supply Chain Project
Project Objective
Improve Overall Equipment Effectiveness (OEE) on a high-speed primary packaging line by
systematically eliminating the Six Big Losses using a Total Productive Maintenance (TPM)
framework, translating equipment reliability gains into supply chain throughput, cost, and
service-level improvement.
Scope
One high-speed packaging line, ideal run rate 100 packs/minute, running 3 shifts x 24/7.
12-week study: Weeks 1-4 Baseline diagnostics, Weeks 5-8 TPM Implementation, Weeks 9-12 Improved/Sustain.
Methodology
1. Baseline: capture daily downtime, output and reject data; calculate Availability, Performance, Quality, OEE.
2. Loss analysis: Pareto the Six Big Losses to prioritize the vital few loss categories.
3. Root cause: 5-Why / Fishbone on top losses (breakdowns, changeovers, minor stops).
4. TPM deployment: Autonomous Maintenance, Planned Maintenance, Kaizen (SMED), Quality Maintenance, Training.
5. Sustain: visual management, single-point lessons, and daily OEE tracking on the shop-floor dashboard.
How to Use This Workbook
Raw_Data - daily input data (blue cells are the only hardcoded inputs; all else is formula-driven).
Assumptions - rate, cost and target assumptions used across all calculations.
OEE_Calc - daily Availability / Performance / Quality / OEE, plus weekly roll-up.
Six_Big_Losses- Pareto of loss categories in equivalent minutes.
TPM_Actions - TPM pillar action tracker (root cause -> countermeasure -> owner -> impact).
Dashboard - executive dashboard with KPIs and charts (use this in the interview walkthrough).
Results_Summary - baseline vs improved comparison, financial impact, and talking points.
Note: all production figures are illustrative/simulated for interview preparation, built to reflect realistic FMCG high-speed line performance.

## Assumptions
Assumptions & Targets
Key inputs referenced by every calculation sheet (edit the blue cells)
Assumption | Value | Unit | Notes
Ideal Run Rate | 100 | packs/min | Design/nameplate speed of the high-speed line
Planned Production Time | 1380 | min/day | 24-hr operation less scheduled breaks/meetings (60 min)
World-Class OEE Target | 85% | % | Common industry benchmark (Nakajima)
Cost per Minute of Downtime | 50 | $/min | Lost production value: line rate x contribution margin/unit
Cost per Rejected Unit | 0.15 | $/unit | Material + packaging + rework cost per rejected pack
Operating Days per Year | 350 | days/yr | Continuous operation, excl. planned shutdowns

## Raw_Data
Raw Production Data
Daily line data — blue cells are inputs; grey cells are formulas
Date | Week | Phase | Planned Time (min) | Breakdown (min) | Changeover/Setup (min) | Minor Stops (min) | Total Downtime (min) | Operating Time (min) | Total Pieces | Reject Pieces | Good Pieces
2025-01-06 | 1 | Baseline | 1380 | 121 | 73.9 | 59.5 | 254.4 | 1125.6 | 100231 | 4894 | 95337
2025-01-07 | 1 | Baseline | 1380 | 112.2 | 87.6 | 60.4 | 260.2 | 1119.8 | 95252 | 5021 | 90231
2025-01-08 | 1 | Baseline | 1380 | 109.4 | 71.3 | 56.7 | 237.4 | 1142.6 | 93891 | 3885 | 90006
2025-01-09 | 1 | Baseline | 1380 | 108.3 | 66.9 | 57.2 | 232.4 | 1147.6 | 96614 | 4148 | 92466
2025-01-10 | 1 | Baseline | 1380 | 132.6 | 73.2 | 55.5 | 261.3 | 1118.7 | 93024 | 4398 | 88626
2025-01-11 | 1 | Baseline | 1380 | 116.3 | 65.8 | 57.6 | 239.7 | 1140.3 | 96691 | 4694 | 91997
2025-01-12 | 1 | Baseline | 1380 | 107.8 | 89.8 | 54.9 | 252.5 | 1127.5 | 94580 | 5118 | 89462
2025-01-13 | 2 | Baseline | 1380 | 94 | 73 | 38.6 | 205.6 | 1174.4 | 98735 | 4765 | 93970
2025-01-14 | 2 | Baseline | 1380 | 117.5 | 72.7 | 51.5 | 241.7 | 1138.3 | 98037 | 3910 | 94127
2025-01-15 | 2 | Baseline | 1380 | 100 | 67.7 | 59.7 | 227.4 | 1152.6 | 100758 | 3875 | 96883
2025-01-16 | 2 | Baseline | 1380 | 112.5 | 68.3 | 47.5 | 228.3 | 1151.7 | 101289 | 5310 | 95979
2025-01-17 | 2 | Baseline | 1380 | 119.8 | 64.6 | 50.1 | 234.5 | 1145.5 | 100099 | 5220 | 94879
2025-01-18 | 2 | Baseline | 1380 | 102.9 | 69.9 | 44.5 | 217.3 | 1162.7 | 98057 | 5034 | 93023
2025-01-19 | 2 | Baseline | 1380 | 124.9 | 70.8 | 59.3 | 255 | 1125 | 98382 | 4333 | 94049
2025-01-20 | 3 | Baseline | 1380 | 106.6 | 80 | 49.3 | 235.9 | 1144.1 | 103634 | 3259 | 100375
2025-01-21 | 3 | Baseline | 1380 | 112.1 | 68.4 | 47.5 | 228 | 1152 | 100958 | 3494 | 97464
2025-01-22 | 3 | Baseline | 1380 | 99.6 | 70.6 | 59.9 | 230.1 | 1149.9 | 99371 | 4025 | 95346
2025-01-23 | 3 | Baseline | 1380 | 96.3 | 75.1 | 51.8 | 223.2 | 1156.8 | 99946 | 4709 | 95237
2025-01-24 | 3 | Baseline | 1380 | 103.4 | 75.5 | 44.6 | 223.5 | 1156.5 | 100379 | 4275 | 96104
2025-01-25 | 3 | Baseline | 1380 | 84.7 | 70.1 | 51.4 | 206.2 | 1173.8 | 102668 | 4453 | 98215
2025-01-26 | 3 | Baseline | 1380 | 85.3 | 64.4 | 47.1 | 196.8 | 1183.2 | 101578 | 4443 | 97135
2025-01-27 | 4 | Baseline | 1380 | 100.8 | 79.2 | 48 | 228 | 1152 | 102181 | 4235 | 97946
2025-01-28 | 4 | Baseline | 1380 | 72.9 | 63.9 | 47.2 | 184 | 1196 | 111357 | 4550 | 106807
2025-01-29 | 4 | Baseline | 1380 | 99.5 | 63.8 | 38.6 | 201.9 | 1178.1 | 106573 | 4857 | 101716
2025-01-30 | 4 | Baseline | 1380 | 105.4 | 56.8 | 56.6 | 218.8 | 1161.2 | 99136 | 4437 | 94699
2025-01-31 | 4 | Baseline | 1380 | 122.2 | 56.2 | 42.9 | 221.3 | 1158.7 | 102415 | 4025 | 98390
2025-02-01 | 4 | Baseline | 1380 | 77.3 | 64.6 | 39.4 | 181.3 | 1198.7 | 106837 | 3977 | 102860
2025-02-02 | 4 | Baseline | 1380 | 114.5 | 57.8 | 44.6 | 216.9 | 1163.1 | 104457 | 3725 | 100732
2025-02-03 | 5 | Implementation | 1380 | 92.3 | 70.9 | 32.8 | 196 | 1184 | 105703 | 4269 | 101434
2025-02-04 | 5 | Implementation | 1380 | 98.9 | 50.6 | 34.8 | 184.3 | 1195.7 | 107554 | 4364 | 103190
2025-02-05 | 5 | Implementation | 1380 | 92.6 | 63.2 | 39.3 | 195.1 | 1184.9 | 105898 | 4295 | 101603
2025-02-06 | 5 | Implementation | 1380 | 81 | 75.4 | 47.4 | 203.8 | 1176.2 | 101776 | 4313 | 97463
2025-02-07 | 5 | Implementation | 1380 | 77.8 | 66.8 | 52.2 | 196.8 | 1183.2 | 103255 | 4534 | 98721
2025-02-08 | 5 | Implementation | 1380 | 94.5 | 67 | 57.4 | 218.9 | 1161.1 | 102663 | 3626 | 99037
2025-02-09 | 5 | Implementation | 1380 | 78.9 | 53.9 | 43.6 | 176.4 | 1203.6 | 107837 | 4365 | 103472
2025-02-10 | 6 | Implementation | 1380 | 93.1 | 56.9 | 51.5 | 201.5 | 1178.5 | 105007 | 5247 | 99760
2025-02-11 | 6 | Implementation | 1380 | 90.7 | 50 | 33.9 | 174.6 | 1205.4 | 109218 | 3850 | 105368
2025-02-12 | 6 | Implementation | 1380 | 91.7 | 60.6 | 40.9 | 193.2 | 1186.8 | 104370 | 3005 | 101365
2025-02-13 | 6 | Implementation | 1380 | 77.8 | 63.7 | 42.9 | 184.4 | 1195.6 | 104194 | 3879 | 100315
2025-02-14 | 6 | Implementation | 1380 | 87.8 | 49.7 | 42.4 | 179.9 | 1200.1 | 107704 | 3301 | 104403
2025-02-15 | 6 | Implementation | 1380 | 87.5 | 61.3 | 48.9 | 197.7 | 1182.3 | 108467 | 3197 | 105270
2025-02-16 | 6 | Implementation | 1380 | 71.9 | 60.9 | 45 | 177.8 | 1202.2 | 108997 | 6063 | 102934
2025-02-17 | 7 | Implementation | 1380 | 83.7 | 62.3 | 45.3 | 191.3 | 1188.7 | 108968 | 3494 | 105474
2025-02-18 | 7 | Implementation | 1380 | 85.9 | 47 | 37 | 169.9 | 1210.1 | 108174 | 3683 | 104491
2025-02-19 | 7 | Implementation | 1380 | 104.6 | 38.2 | 43.4 | 186.2 | 1193.8 | 104019 | 3253 | 100766
2025-02-20 | 7 | Implementation | 1380 | 89.9 | 53.7 | 31.1 | 174.7 | 1205.3 | 107193 | 3970 | 103223
2025-02-21 | 7 | Implementation | 1380 | 68.1 | 54.9 | 39 | 162 | 1218 | 108483 | 4812 | 103671
2025-02-22 | 7 | Implementation | 1380 | 84.4 | 37 | 39.9 | 161.3 | 1218.7 | 108509 | 4112 | 104397
2025-02-23 | 7 | Implementation | 1380 | 67.3 | 52.3 | 42.2 | 161.8 | 1218.2 | 112196 | 3101 | 109095
2025-02-24 | 8 | Implementation | 1380 | 66.4 | 45.7 | 31.3 | 143.4 | 1236.6 | 116998 | 3853 | 113145
2025-02-25 | 8 | Implementation | 1380 | 55.3 | 56.9 | 50.8 | 163 | 1217 | 113373 | 2643 | 110730
2025-02-26 | 8 | Implementation | 1380 | 64.6 | 59.7 | 31 | 155.3 | 1224.7 | 112648 | 3918 | 108730
2025-02-27 | 8 | Implementation | 1380 | 59.3 | 49.1 | 13.2 | 121.6 | 1258.4 | 112049 | 3322 | 108727
2025-02-28 | 8 | Implementation | 1380 | 55.5 | 62.6 | 25.9 | 144 | 1236 | 111502 | 3519 | 107983
2025-03-01 | 8 | Implementation | 1380 | 87.7 | 38.1 | 44.1 | 169.9 | 1210.1 | 110258 | 2867 | 107391
2025-03-02 | 8 | Implementation | 1380 | 76 | 51.1 | 31.7 | 158.8 | 1221.2 | 111407 | 3229 | 108178
2025-03-03 | 9 | Improved | 1380 | 65.5 | 51.2 | 44.3 | 161 | 1219 | 108914 | 4231 | 104683
2025-03-04 | 9 | Improved | 1380 | 40.7 | 44.7 | 37.3 | 122.7 | 1257.3 | 116153 | 2912 | 113241
2025-03-05 | 9 | Improved | 1380 | 61.6 | 42 | 29.1 | 132.7 | 1247.3 | 116652 | 3496 | 113156
2025-03-06 | 9 | Improved | 1380 | 55.8 | 53.1 | 35.3 | 144.2 | 1235.8 | 115477 | 3618 | 111859
2025-03-07 | 9 | Improved | 1380 | 54.1 | 41.4 | 38.4 | 133.9 | 1246.1 | 115928 | 3255 | 112673
2025-03-08 | 9 | Improved | 1380 | 65.5 | 56.1 | 29 | 150.6 | 1229.4 | 114220 | 3103 | 111117
2025-03-09 | 9 | Improved | 1380 | 61.5 | 54.7 | 39 | 155.2 | 1224.8 | 114457 | 3973 | 110484
2025-03-10 | 10 | Improved | 1380 | 58 | 47.7 | 28.3 | 134 | 1246 | 116120 | 2880 | 113240
2025-03-11 | 10 | Improved | 1380 | 58.9 | 47 | 24.7 | 130.6 | 1249.4 | 120850 | 2468 | 118382
2025-03-12 | 10 | Improved | 1380 | 43.2 | 51.5 | 36 | 130.7 | 1249.3 | 117177 | 3351 | 113826
2025-03-13 | 10 | Improved | 1380 | 57.6 | 35.1 | 31 | 123.7 | 1256.3 | 114567 | 3475 | 111092
2025-03-14 | 10 | Improved | 1380 | 56 | 35.7 | 28.2 | 119.9 | 1260.1 | 117663 | 2663 | 115000
2025-03-15 | 10 | Improved | 1380 | 47.9 | 44.2 | 32.2 | 124.3 | 1255.7 | 114941 | 2655 | 112286
2025-03-16 | 10 | Improved | 1380 | 60.5 | 30.7 | 20.6 | 111.8 | 1268.2 | 115544 | 2818 | 112726
2025-03-17 | 11 | Improved | 1380 | 55.1 | 50.4 | 33.7 | 139.2 | 1240.8 | 115330 | 2610 | 112720
2025-03-18 | 11 | Improved | 1380 | 39.3 | 38.5 | 25.7 | 103.5 | 1276.5 | 119884 | 2229 | 117655
2025-03-19 | 11 | Improved | 1380 | 57.6 | 50.9 | 27 | 135.5 | 1244.5 | 117082 | 3065 | 114017
2025-03-20 | 11 | Improved | 1380 | 46.5 | 40.4 | 27.8 | 114.7 | 1265.3 | 118256 | 2231 | 116025
2025-03-21 | 11 | Improved | 1380 | 51.7 | 42.6 | 37.9 | 132.2 | 1247.8 | 118783 | 3978 | 114805
2025-03-22 | 11 | Improved | 1380 | 42.2 | 45.6 | 29 | 116.8 | 1263.2 | 123356 | 2305 | 121051
2025-03-23 | 11 | Improved | 1380 | 41.3 | 33.8 | 12.9 | 88 | 1292 | 119151 | 2256 | 116895
2025-03-24 | 12 | Improved | 1380 | 46.8 | 37.7 | 38.1 | 122.6 | 1257.4 | 120579 | 2064 | 118515
2025-03-25 | 12 | Improved | 1380 | 34.2 | 38.9 | 15.8 | 88.9 | 1291.1 | 126091 | 3265 | 122826
2025-03-26 | 12 | Improved | 1380 | 39.4 | 21.3 | 34.5 | 95.2 | 1284.8 | 120482 | 3155 | 117327
2025-03-27 | 12 | Improved | 1380 | 25.9 | 30.2 | 25 | 81.1 | 1298.9 | 122218 | 2169 | 120049
2025-03-28 | 12 | Improved | 1380 | 52.5 | 26.5 | 24 | 103 | 1277 | 120351 | 2717 | 117634
2025-03-29 | 12 | Improved | 1380 | 53.5 | 26 | 14.3 | 93.8 | 1286.2 | 124189 | 2690 | 121499
2025-03-30 | 12 | Improved | 1380 | 36 | 47.4 | 25.8 | 109.2 | 1270.8 | 122449 | 2490 | 119959

## OEE_Calc
OEE Calculation Engine
Availability x Performance x Quality — fully formula-driven from Raw_Data
Date | Week | Phase | Availability | Performance | Quality | OEE | Speed Loss (min) | Quality Loss (min)
2025-01-06 | 1 | Baseline | 81.57% | 89.05% | 95.12% | 69.08% | 123.29 | 48.94
2025-01-07 | 1 | Baseline | 81.14% | 85.06% | 94.73% | 65.38% | 167.28 | 50.21
2025-01-08 | 1 | Baseline | 82.8% | 82.17% | 95.86% | 65.22% | 203.69 | 38.85
2025-01-09 | 1 | Baseline | 83.16% | 84.19% | 95.71% | 67% | 181.46 | 41.48
2025-01-10 | 1 | Baseline | 81.07% | 83.15% | 95.27% | 64.22% | 188.46 | 43.98
2025-01-11 | 1 | Baseline | 82.63% | 84.79% | 95.15% | 66.66% | 173.39 | 46.94
2025-01-12 | 1 | Baseline | 81.7% | 83.88% | 94.59% | 64.83% | 181.7 | 51.18
2025-01-13 | 2 | Baseline | 85.1% | 84.07% | 95.17% | 68.09% | 187.05 | 47.65
2025-01-14 | 2 | Baseline | 82.49% | 86.13% | 96.01% | 68.21% | 157.93 | 39.1
2025-01-15 | 2 | Baseline | 83.52% | 87.42% | 96.15% | 70.21% | 145.02 | 38.75
2025-01-16 | 2 | Baseline | 83.46% | 87.95% | 94.76% | 69.55% | 138.81 | 53.1
2025-01-17 | 2 | Baseline | 83.01% | 87.38% | 94.79% | 68.75% | 144.51 | 52.2
2025-01-18 | 2 | Baseline | 84.25% | 84.34% | 94.87% | 67.41% | 182.13 | 50.34
2025-01-19 | 2 | Baseline | 81.52% | 87.45% | 95.6% | 68.15% | 141.18 | 43.33
2025-01-20 | 3 | Baseline | 82.91% | 90.58% | 96.86% | 72.74% | 107.76 | 32.59
2025-01-21 | 3 | Baseline | 83.48% | 87.64% | 96.54% | 70.63% | 142.42 | 34.94
2025-01-22 | 3 | Baseline | 83.33% | 86.42% | 95.95% | 69.09% | 156.19 | 40.25
2025-01-23 | 3 | Baseline | 83.83% | 86.4% | 95.29% | 69.01% | 157.34 | 47.09
2025-01-24 | 3 | Baseline | 83.8% | 86.8% | 95.74% | 69.64% | 152.71 | 42.75
2025-01-25 | 3 | Baseline | 85.06% | 87.47% | 95.66% | 71.17% | 147.12 | 44.53
2025-01-26 | 3 | Baseline | 85.74% | 85.85% | 95.63% | 70.39% | 167.42 | 44.43
2025-01-27 | 4 | Baseline | 83.48% | 88.7% | 95.86% | 70.98% | 130.19 | 42.35
2025-01-28 | 4 | Baseline | 86.67% | 93.11% | 95.91% | 77.4% | 82.43 | 45.5
2025-01-29 | 4 | Baseline | 85.37% | 90.46% | 95.44% | 73.71% | 112.37 | 48.57
2025-01-30 | 4 | Baseline | 84.14% | 85.37% | 95.52% | 68.62% | 169.84 | 44.37
2025-01-31 | 4 | Baseline | 83.96% | 88.39% | 96.07% | 71.3% | 134.55 | 40.25
2025-02-01 | 4 | Baseline | 86.86% | 89.13% | 96.28% | 74.54% | 130.33 | 39.77
2025-02-02 | 4 | Baseline | 84.28% | 89.81% | 96.43% | 72.99% | 118.53 | 37.25
2025-02-03 | 5 | Implementation | 85.8% | 89.28% | 95.96% | 73.5% | 126.97 | 42.69
2025-02-04 | 5 | Implementation | 86.64% | 89.95% | 95.94% | 74.78% | 120.16 | 43.64
2025-02-05 | 5 | Implementation | 85.86% | 89.37% | 95.94% | 73.63% | 125.92 | 42.95
2025-02-06 | 5 | Implementation | 85.23% | 86.53% | 95.76% | 70.63% | 158.44 | 43.13
2025-02-07 | 5 | Implementation | 85.74% | 87.27% | 95.61% | 71.54% | 150.65 | 45.34
2025-02-08 | 5 | Implementation | 84.14% | 88.42% | 96.47% | 71.77% | 134.47 | 36.26
2025-02-09 | 5 | Implementation | 87.22% | 89.6% | 95.95% | 74.98% | 125.23 | 43.65
2025-02-10 | 6 | Implementation | 85.4% | 89.1% | 95% | 72.29% | 128.43 | 52.47
2025-02-11 | 6 | Implementation | 87.35% | 90.61% | 96.47% | 76.35% | 113.22 | 38.5
2025-02-12 | 6 | Implementation | 86% | 87.94% | 97.12% | 73.45% | 143.1 | 30.05
2025-02-13 | 6 | Implementation | 86.64% | 87.15% | 96.28% | 72.69% | 153.66 | 38.79
2025-02-14 | 6 | Implementation | 86.96% | 89.75% | 96.94% | 75.65% | 123.06 | 33.01
2025-02-15 | 6 | Implementation | 85.67% | 91.74% | 97.05% | 76.28% | 97.63 | 31.97
2025-02-16 | 6 | Implementation | 87.12% | 90.66% | 94.44% | 74.59% | 112.23 | 60.63
2025-02-17 | 7 | Implementation | 86.14% | 91.67% | 96.79% | 76.43% | 99.02 | 34.94
2025-02-18 | 7 | Implementation | 87.69% | 89.39% | 96.6% | 75.72% | 128.36 | 36.83
2025-02-19 | 7 | Implementation | 86.51% | 87.13% | 96.87% | 73.02% | 153.61 | 32.53
2025-02-20 | 7 | Implementation | 87.34% | 88.93% | 96.3% | 74.8% | 133.37 | 39.7
2025-02-21 | 7 | Implementation | 88.26% | 89.07% | 95.56% | 75.12% | 133.17 | 48.12
2025-02-22 | 7 | Implementation | 88.31% | 89.04% | 96.21% | 75.65% | 133.61 | 41.12
2025-02-23 | 7 | Implementation | 88.28% | 92.1% | 97.24% | 79.05% | 96.24 | 31.01
2025-02-24 | 8 | Implementation | 89.61% | 94.61% | 96.71% | 81.99% | 66.62 | 38.53
2025-02-25 | 8 | Implementation | 88.19% | 93.16% | 97.67% | 80.24% | 83.27 | 26.43
2025-02-26 | 8 | Implementation | 88.75% | 91.98% | 96.52% | 78.79% | 98.22 | 39.18
2025-02-27 | 8 | Implementation | 91.19% | 89.04% | 97.04% | 78.79% | 137.91 | 33.22
2025-02-28 | 8 | Implementation | 89.57% | 90.21% | 96.84% | 78.25% | 120.98 | 35.19
2025-03-01 | 8 | Implementation | 87.69% | 91.11% | 97.4% | 77.82% | 107.52 | 28.67
2025-03-02 | 8 | Implementation | 88.49% | 91.23% | 97.1% | 78.39% | 107.13 | 32.29
2025-03-03 | 9 | Improved | 88.33% | 89.35% | 96.12% | 75.86% | 129.86 | 42.31
2025-03-04 | 9 | Improved | 91.11% | 92.38% | 97.49% | 82.06% | 95.77 | 29.12
2025-03-05 | 9 | Improved | 90.38% | 93.52% | 97% | 82% | 80.78 | 34.96
2025-03-06 | 9 | Improved | 89.55% | 93.44% | 96.87% | 81.06% | 81.03 | 36.18
2025-03-07 | 9 | Improved | 90.3% | 93.03% | 97.19% | 81.65% | 86.82 | 32.55
2025-03-08 | 9 | Improved | 89.09% | 92.91% | 97.28% | 80.52% | 87.2 | 31.03
2025-03-09 | 9 | Improved | 88.75% | 93.45% | 96.53% | 80.06% | 80.23 | 39.73
2025-03-10 | 10 | Improved | 90.29% | 93.19% | 97.52% | 82.06% | 84.8 | 28.8
2025-03-11 | 10 | Improved | 90.54% | 96.73% | 97.96% | 85.78% | 40.9 | 24.68
2025-03-12 | 10 | Improved | 90.53% | 93.79% | 97.14% | 82.48% | 77.53 | 33.51
2025-03-13 | 10 | Improved | 91.04% | 91.19% | 96.97% | 80.5% | 110.63 | 34.75
2025-03-14 | 10 | Improved | 91.31% | 93.38% | 97.74% | 83.33% | 83.47 | 26.63
2025-03-15 | 10 | Improved | 90.99% | 91.54% | 97.69% | 81.37% | 106.29 | 26.55
2025-03-16 | 10 | Improved | 91.9% | 91.11% | 97.56% | 81.69% | 112.76 | 28.18
2025-03-17 | 11 | Improved | 89.91% | 92.95% | 97.74% | 81.68% | 87.5 | 26.1
2025-03-18 | 11 | Improved | 92.5% | 93.92% | 98.14% | 85.26% | 77.66 | 22.29
2025-03-19 | 11 | Improved | 90.18% | 94.08% | 97.38% | 82.62% | 73.68 | 30.65
2025-03-20 | 11 | Improved | 91.69% | 93.46% | 98.11% | 84.08% | 82.74 | 22.31
2025-03-21 | 11 | Improved | 90.42% | 95.19% | 96.65% | 83.19% | 59.97 | 39.78
2025-03-22 | 11 | Improved | 91.54% | 97.65% | 98.13% | 87.72% | 29.64 | 23.05
2025-03-23 | 11 | Improved | 93.62% | 92.22% | 98.11% | 84.71% | 100.49 | 22.56
2025-03-24 | 12 | Improved | 91.12% | 95.9% | 98.29% | 85.88% | 51.61 | 20.64
2025-03-25 | 12 | Improved | 93.56% | 97.66% | 97.41% | 89% | 30.19 | 32.65
2025-03-26 | 12 | Improved | 93.1% | 93.77% | 97.38% | 85.02% | 79.98 | 31.55
2025-03-27 | 12 | Improved | 94.12% | 94.09% | 98.23% | 86.99% | 76.72 | 21.69
2025-03-28 | 12 | Improved | 92.54% | 94.25% | 97.74% | 85.24% | 73.49 | 27.17
2025-03-29 | 12 | Improved | 93.2% | 96.55% | 97.83% | 88.04% | 44.31 | 26.9
2025-03-30 | 12 | Improved | 92.09% | 96.36% | 97.97% | 86.93% | 46.31 | 24.9
Weekly Roll-Up
Week | Phase | Avg Availability | Avg Performance | Avg Quality | Avg OEE | Target
1 | Baseline | 82.01% | 84.61% | 95.2% | 66.06% | 85%
2 | Baseline | 83.34% | 86.39% | 95.33% | 68.62% | 85%
3 | Baseline | 84.02% | 87.31% | 95.95% | 70.38% | 85%
4 | Baseline | 84.97% | 89.28% | 95.93% | 72.79% | 85%
5 | Implementation | 85.8% | 88.63% | 95.95% | 72.97% | 85%
6 | Implementation | 86.45% | 89.56% | 96.19% | 74.47% | 85%
7 | Implementation | 87.5% | 89.62% | 96.51% | 75.68% | 85%
8 | Implementation | 89.07% | 91.62% | 97.04% | 79.18% | 85%
9 | Improved | 89.64% | 92.58% | 96.93% | 80.46% | 85%
10 | Improved | 90.94% | 92.99% | 97.51% | 82.46% | 85%
11 | Improved | 91.41% | 94.21% | 97.75% | 84.18% | 85%
12 | Improved | 92.82% | 95.51% | 97.84% | 86.73% | 85%
Phase Summary
Phase | Avg Availability | Avg Performance | Avg Quality | Avg OEE
Baseline | 83.58% | 86.9% | 95.61% | 69.46%
Implementation | 87.21% | 89.86% | 96.42% | 75.58%
Improved | 91.2% | 93.82% | 97.51% | 83.46%

## Six_Big_Losses
Six Big Losses — Pareto Analysis
Total equivalent-minutes lost by category over the 12-week study (used to prioritize TPM action)
Loss Category | OEE Bucket | Total Loss (min) | % of Total | Cumulative %
Reduced Speed (Speed Loss) | Performance | 9809.66 | 35.51% | 35.51%
Equipment Breakdowns | Availability | 6633.8 | 24.01% | 59.52%
Changeover / Setup | Availability | 4686.7 | 16.96% | 76.48%
Minor Stops / Idling | Availability | 3365.7 | 12.18% | 88.66%
Quality Defects / Rework | Quality | 3132.75 | 11.34% | 100%
Total |  | 27628.61

## TPM_Actions
TPM Pillar Action Tracker
Root-cause countermeasures deployed by TPM pillar, mapped to OEE impact
TPM Pillar | Loss / Problem Identified | Root Cause (5-Why) | Countermeasure (Kaizen) | Owner | Target Date | Status | OEE Impact
Autonomous Maintenance | Frequent minor stops on infeed conveyor | Operators not trained to detect early wear; no cleaning/inspection standard | Implemented CIL (Clean-Inspect-Lubricate) checklist + operator ownership of infeed zone | Line Operators / Shift Lead | Week 5 | Complete | +3.0 pp Availability
Planned Maintenance | Recurring gearbox breakdowns on wrapper | Time-based PM interval too long vs. actual duty cycle; no vibration monitoring | Shifted to condition-based maintenance; added vibration sensors + shortened PM interval | Maintenance Engineer | Week 6 | Complete | +4.5 pp Availability
Focused Improvement (Kaizen) | Long product changeovers (avg 75 min) | Internal steps done while line stopped; tools not staged in advance | SMED workshop: converted internal to external setup, pre-staged tool kits, one-touch clamps | Industrial Engineer | Week 6 | Complete | -40 min/changeover
Quality Maintenance | Reject rate elevated at wrapper seal station | Seal temperature drift not detected until downstream inspection | Added inline seal-integrity sensor with real-time alarm; SPC control chart on seal temp | Quality Engineer | Week 7 | Complete | -2.5 pp Reject Rate
Planned Maintenance | Bearing failures causing unplanned stops | No lubrication schedule tied to run-hours; generic OEM interval used | Built run-hour-based lubrication schedule with tagged lube points and checklist | Maintenance Planner | Week 7 | Complete | +1.8 pp Availability
Education & Training | Inconsistent changeover execution across shifts | No standard work / visual aid; tribal knowledge only with senior operators | Created One-Point Lessons (OPLs) and changeover SOP with visual step cards | Training Coordinator | Week 8 | Complete | Reduced changeover variability
Focused Improvement (Kaizen) | Speed losses from micro-jams on flow wrapper | Film tension inconsistent; guide rails mis-aligned after changeover | Standardized film tension settings; added laser-guided rail alignment fixture | Process Engineer | Week 9 | Complete | +3.0 pp Performance
Early Equipment Management | New SKU changeovers still slow despite SMED | Tooling for new SKUs not designed for quick-change compatibility | Fed learnings back to engineering spec for next tooling purchase (DFM for changeover) | Engineering Lead | Week 10 | In Progress | Future-proofing (no direct pp yet)
Safety, Health & Environment | Autonomous maintenance tasks introduced new pinch-point exposure | CIL tasks required access to guarded zones without a safe isolation step | Added LOTO step to CIL checklist and interlock guarding on infeed access panel | EHS Coordinator | Week 8 | Complete | Zero recordable incidents maintained
Office TPM | Downtime data entered manually with 1-2 day lag | No real-time link between line PLC and OEE tracking sheet | Automated downtime/output data feed from line PLC to OEE tracker (foundation for this dashboard) | Continuous Improvement Lead | Week 9 | Complete | Real-time visibility enabled

## Results_Summary
Results Summary & Financial Impact
Baseline vs. Improved comparison — ready for interview walkthrough
Baseline vs. Improved Performance
Metric | Baseline (Wks 1-4) | Improved (Wks 9-12) | Change (pp / abs)
Availability | 83.58% | 91.2% | 7.621%
Performance | 86.9% | 93.82% | 6.926%
Quality | 95.61% | 97.51% | 1.901%
OEE | 69.46% | 83.46% | 13.99%
Financial & Operational Impact (Annualized)
Impact Driver | Value | Calculation Basis
Downtime Reduced (min/day) | 105.1643 | Avg total downtime/day, Baseline (Wks1-4) minus Improved (Wks9-12)
Extra Good Output Capacity (packs/day) | 17847.6429 | Avg total pieces/day, Improved minus Baseline
Annualized Downtime Cost Avoidance | 1840375 | Downtime saved/day x Cost per minute x Operating days/year
Annualized Reject/Waste Cost Avoidance | 76775.625 | Reject units/day reduced x Cost per reject unit x Operating days/year
Total Estimated Annualized Savings | 1917150.625 | Downtime cost avoidance + reject/waste cost avoidance
Interview Talking Points (STAR Format)
Situation | A high-speed packaging line was running below industry benchmark OEE (~68%), driven by frequent breakdowns, long changeovers, and inconsistent quality — constraining throughput and putting service levels and case-fill rate at risk.
Task | Lead a structured OEE improvement initiative using the TPM framework to identify the vital-few losses, deploy root-cause countermeasures, and lift OEE toward the 85% world-class benchmark without capital investment in new equipment.
Action | Built a daily OEE tracking model (Availability/Performance/Quality); ran a Pareto on the Six Big Losses to prioritize breakdowns, changeovers, and minor stops; deployed Autonomous Maintenance (CIL) and Planned/Predictive Maintenance to cut unplanned downtime; ran a SMED kaizen to cut changeover time; added inline quality sensing to reduce rework; and stood up a visual, real-time OEE dashboard to sustain the gains.
Result | OEE improved from ~68% (Baseline) to ~82% (Improved) over 12 weeks — a +14 percentage-point gain — reducing changeovers by ~40 minutes each, cutting reject rate by more than half, and unlocking an estimated six-figure annualized cost avoidance in downtime and waste, directly improving line capacity available to the supply chain plan.
Likely Interview Questions to Prepare
• Walk me through how you calculated OEE and why Availability x Performance x Quality, not a simple average.
• How did you decide which losses to attack first? (Pareto principle — vital few vs. trivial many)
• What would you do differently if the top loss had been Quality instead of Availability?
• How do you sustain the gains after the project team moves on? (visual management, OPLs, layered audits)
• How does line-level OEE improvement translate into supply chain KPIs (case fill rate, OTIF, inventory buffers)?
• If Finance challenged your cost-avoidance number, how would you defend the $/minute downtime assumption?